## Year 2 Action Planning (2024)
#WePaddleTogether - A Strategy for Equality, Diversity and Inclusion - Paddle UK (formerly British Canoeing) DIAP Submission
Ambition 1: Engaging recreational paddlers and attracting new paddlers
Strategic action |  | Year 2 Action Planning | RAG Rating | Responsible party | Timescale | Comments
1 | We will create and activate partnerships, campaigns and targeted programmes to attract new participants from under-represented groups to increase diversity in the paddling community (from 2023) | We will continue to grow the #ShePaddles club champion programme and support the delivery of #ShePaddles events. 15 new Aqua Paddle venues across England are due to be added. Three Padding with Pride events will be delivered by Delivery Partners. Engagement with Active Thames for the provision of at least three community paddling projects. |  | Rcereational Programmes Lead Programmes Support Officer | 2024-10-01 | #ShePaddles champion club showing positive growth, AquaPaddle venues coming on board, One Pride Paddle (Birmingham) confirmed, 10 Active Thames paddlesport projects recieved funding for 2024 delivery.
2 | More opportunities for people with a range of disabilities to paddle will be created, through the delivery of disability-specific programmes and improved accessibility to paddling opportunities (from 2023) | We will develop a Disability Champion club programme and related resources. This will be supported by additional investment into the delivery of a disability action plan, focused on audit and insight at this stage, culminating in a disability specific programme. |  | Recreational Programmes Lead | 2024-10-01 | Currently struggling to appoint a service provider to deliver this piece of work for us
3 | We will identify core cities with a range of local and regional partners to establish Community Paddling Hubs, which provide local and accessible paddling opportunities (from 2022) | We will establish and affiliate 10 new community paddling hubs, spread across Birmingham, London, Manchester, Gloucester, and Lancashire. |  | Recreational Programmes Lead | 2024-10-01 | 6 projects in play with 9 other potenital groups engaging with us
4 | The quality and amount of equality monitoring data will be improved to understand the reach of programmes and initiatives run by Paddle UK to engage recreational paddlers and attract new paddlers (from 2023) | Equality monitoring data will be gathered for all programme recruitment and external partners will be supported to gather equality data. Insight will be shared and analysed. |  | Recreational Programmes Lead | 2024-10-01 | This project is on track, the next phase of #ShePaddles bursaries now have equality monitoring questions embedded.
Ambition 2: Increasing membership and improving member services
Strategic action |  | Year 2 Action Planning | RAG Rating | Responsible party | Timescale | Comments
1 | Insight into the views, demographics and interests of our members will be improved through enhanced tracking, data collection and surveys | We will introduce a diverse and representative Members Panel to gain insight through additional surveys and polls, and develop an annual survey plan for 2024 to ensure relevant insight is captured. |  | Head of Membership and Partnerships | 2024-10-01 | The Equality monitoring questions have been updated to include a Prefer Not to Say option for every question. These questions have been made mandatory to improve completion rates.
2 | We will continue to review and identify opportunities to embed inclusive opportunities into the membership offering, such as through Carers Membership, youth and family memberships | We will promote the Carers Membership during 2024 across social media and use a case study in Members News as part of the Paddlers Spotlight series. We will additionally complete a fit-for-purpose review of the Family Membership categories. |  | Head of Membership and Partnerships | 2024-10-02 | Carer's membership is live and the CS Team are aware of it, and able to promote it during calls and emails with members. Alter the Couples membership Text to Joint to refresh and update our approach.
3 | We will deliver campaigns and embed approaches which drive the ongoing completion of equality monitoring data in the membership | We will be making equality monitoring data completion a compulsory element of membership regsitration and renewal. This will including embedding reminders on the system for existing members who have not completed this data return. |  | Head of Membership and Partnerships | 2024-10-03
Ambition 3: Promoting places to paddle and environmental awareness
Strategic action |  | Year 2 Action Planning | RAG Rating | Responsible party | Timescale | Comments
1 | We will ensure inclusion themes are highlighted through the updated Clear Access Clear Waters Charter and supported by case studies | In the run up to campaign for a general election in 2024, lived experience stories of people from a diverse range of backgrounds were used to communicate the impact of the Charter will be used to engage with key parliamentary stakeholders. Paddle UK will continue to champion on the Outdoors for All manifesto, with the view to target policy change at the next general election, which we anticipate will be in 2024. |  | Head of Access & Environment | 2024-12-01
2 | We will embed accessibility considerations into trails guidance and the facilities strategy, working closely with the Canoe Foundation on funded projects | The Canoe Foundation will prioritise funding for projects with accessibility and inclusion aims and outcomes. The Canoe Foundation will support Community Hubs through the funding interventions with high deprivation and underrepresented groups. |  | Canoe Foundation Marketing and Fundraising Lead | 2024-12-01
3 | We will ensure that Paddle Points has clear, standardised accessibility information across the tool | We will launch a new template framework for the PaddlePoints tool, supporting the provision of key information for people looking for places to paddle and embedding disability specific information developed from insight consultation from those with lived experience of disability and the IAG. |  | Paddle Trails & Paddle Points Content Lead | 2024-12-01
4 | We will recruit and engage with volunteers from a greater range of backgrounds across the environmental and access programme | We will be engaging with clubs and partners from areas of greater deprivation will be offered early bird opportunities to participate in the Big Paddle Clean Up 2024. |  | Access & Environment Leads | 2024-05-01
|  | Equality data monitoring will be requested from all volunteers involved in environmental and access initiatives. |  | Access & Environment Leads | 2024-12-01
|  | We will be delivering training on invasive species, as well as invasive species clean up events will be running within the Community Hubs delivered in core inner cities, with specific outreach to under-represented communities. |  | Access & Environment Leads | 2024-12-01
Ambition 4: Supporting clubs and delivery partners
Strategic action |  | Year 2 Action Planning | RAG Rating | Responsible party | Timescale | Comments
1 | We will develop and promote the Clubhouse digital platform, to support the work of clubs on a range of issues, including governance, safeguarding and equality, diversity and inclusion | Clubhouse will continue to include inclusion webinars, governance templates and guidance and inclusion resources. We will use the Clubhouse Facebook group to highlight the work of the community paddling hubs with follow up from club support officers on how other clubs can be deliver similar activity. |  | Club Support Officers | 2024-12-01
2 | We will develop an inclusive paddling offer for clubs which supports them to attract and retain paddlers who reflect the diversity of their local community | We will double the proportion of clubs in the club network coming through the Community Paddling Hubs scheme from 2.5% in 2023 to 5% in 2024. A Club Datapage will form part of the new membership system that will highlight to clubs where their opportunities are, and provide support and resources to deliver more inclusive provision. |  | Club Support Officers Recreational Programmes Lead | 2024-12-01
3 | We will support delivery partners in promoting their activities within their local communities, promoting their health benefits and attracting participants from under-represented groups | A series of Delivery Partner Webinars will be delivered in partnership with Inclusive Employers, including; Female Participation - Building Nurturing Networks; Workforce Insight Report 2023; Being Equitable and Inclusive through our Work and Activities; Inclusive communications; Mental health and wellbeing in sport and physical activity sector; LGBTIQ+ inclusion in commercial paddlesport businesses. |  | Head of Membership and Partnerships | 2024-07-01
|  | We will be engaging with ALDI and Money Supermarket Campigns providing opportunities to consumers from a diverse range of backgrounds with access to sports facilities that they may not have had access to, or have knowledge of. |  |  | 2024-07-01
4 | We will continue to deliver learning opportunities for the club and Delivery Partner networks to further their understanding of inclusion topics | In partnership with Inclusive Employers, we will deliver a series of inclusion webinars (minimum of six webinars) for Delivery Partners to support their engagement and understanding of providing inclusive services. |  | Head of Coaching and Partnerships | 2024-07-01
5 | We will share best inclusive practice across the club and Delivery Partner network through case studies to improve engagement with under-represented groups and communities | We will deliver The Delivery Partner Conference as a platform for sharing case studies, as the Conference now runs over six monthly 'Live Days'. We will provide networking opportunities and opportunities for Delivery Partners to share their successes via focus groups with external stakeholders. |  | Coaching Development and Engagement Lead Delivery Centre and Partnerships Lead | 2024-12-01
Ambition 5: Developing and supporting coaches, leaders, instructors and guides
Strategic action |  | Year 2 Action Planning | RAG Rating | Responsible party | Timescale | Comments
1 | More opportunities will be created for continued learning on topics around equality, diversity and inclusion will be continually supported through the online Digital Library resources, based on learner needs | We will launch a neuurodiversity mini-series, developed in partnership with Neurodiverse Sport, in line with Neurodiversity Celebration Week. |  | EDI Lead Digital Learning Lead | 2024-03-01
2 | We will share and spotlight instructors, coaches, leaders and providers from a range of backgrounds and identities to highlight both diversity and examples of good inclusive practice | We will continue to identify appropriate case studies on coaches from a diverse range of backgrounds and promoting wider engagement, across news letters, social media and news items. |  | Coaching Enagement Lead | Ongoing | This is not a task and finish piece of work and needs to be continued throughout a large timescale
3 | We will support deliverers through CPD and other learning opportunities to understand practical, implementable approaches to inclusive practice, that ensures all paddlers can participate in paddling activities | In addition to the series of inclusion webinars for Delivery Partners, we will also deliver a range of CPD webinars as well as podcasts and face-to-face courses with embedded inclusion themes. |  | Head of Membership and Partnerships | 2024-07-01
|  | We will achieve the CIMSPA Training Provider Partner Status to ensure our CPD is widely recognised across the Sport and Physical Activity Sector. |  | Head of Membership and Partnerships | 2024-07-01
4 | We will develop and implement opportunities that encourage and support individuals from under-represented groups to become active coaches, leaders and providers | Alongisde the Delivery Partner webinars, we will also deliver a range of CPD and face to face events with embedded inclusion themes, to ensure that our diverse team of trainers are able to influence the provider network and paddling community. Our April provider campaign is focussed on growing the number of course providers from under-represented backgrounds. |  | Coaching Development and Engagement Lead Delivery Centre and Partnerships Lead | 2024-12-01
Ambition 6: Developing and support volunteers
Strategic action |  | Year 2 Action Planning | RAG Rating | Responsible party | Timescale | Comments
1 | We will provide training and support for volunteers working within clubs and discipline committees in areas including equality, diversity and inclusion | Our new website will have a refreshed 'volunteering' area, creating an accessible area for resources, training and support for volunteers and organisations. |  | Director of Recreational Paddling | Summer 2024
2 | Initiatives will be designed and implemented to encourage more people from diverse backgrounds to become volunteers within the paddling community | Following involvement with the Unified Action Project with YST and Sporting Equals, a Youth Forum with be established. |  | EDI Lead Recreational Programmes Lead Safeguarding Manager | 2024-12-01
3 | We will create more robust systems for the collection of equality monitoring data to understand the demographics of those involved in volunteering in paddling | We will develop a central form to collect volunteer equality monitoring data across initiatives and programmes. |  | EDI Lead | 2024-05-01
4 | We will support volunteers, such as Discipline Committees and club committees, to implement inclusion strategies and initiatives in their communities | We will provide resources and case studies to support inclusion strategies and intitatives in their clubs and organisations. Due to capacity, the focus will be club and wider volunteer support, followed by dedicated support for Discipline Committees. |  | Director of Recreational Paddling | 2024-12-01
Ambition 7: Developing talent and achieving international success
Strategic action |  | Year 2 Action Planning | RAG Rating | Responsible party | Timescale | Comments
1 | We will develop and deliver the talent pathways, national team plan and talent inclusion plan in each of the competition disciplines | Continue to support London Youth Rowing (LYR) Active Paddle programme, explore potential of Active Paddle with LYR in Nottingham, commence delivery of Backing the Best Team Keene talent inclusion project targeting girls from areas of deprivation. |  | Flatwater Pathway Lead | 2024-12-01
2 | We will support the development of more inclusive environments within Talent Club Partners (in Olympic and Paralympic disciplines) through the delivery of the EDI requirements of Quality Club | The Talent Club Partner programme is undergoing review, and current TCPs who are Quality Club compliant will be supported to continue delivery of the programme. The development of Talent Champion Club will support a larger number of talent-oriented clubs to consider the delivery of inclusive settings. |  | Flatwater Pathway Lead Club Support Officers | 2024-12-01
3 | We will gather and monitor appropriate diversity data for programme coaches, those involved in selected Junior GB teams and athletes involved in squad activity | Following the successful piloting of data collection with the GB Talent Squad, we will gather and monitor appropriate diversity data for Olympic and Paralympic GB representative teams, support staff and coaches. |  | Head of Pathways, Competition and Events | 2024-10-01
4 | We will increase the use of equality impact assessments on all major programmes, procurement and recruitment processes and partnership engagement to drive inclusion | We will increase the use of equality impact assessments on all major programmes, procurement and recruitment processes and partnership engagement to drive inclusion |  | Relevant individuals to complete when required | 2024-12-01
5 | We will deliver a fund for athletes requiring financial support and to address socioeconomic inequalities | We will continue to deliver the Athlete Support Fund each year to help address socioeconomic inequalities and complete an Equality Impact Assessment at the end of the annual delivery cycle. |  | Director of Paddlesport | 2024-10-01
Ambition 8: Providing excellent championships, competitions and events
Strategic action |  | Year 2 Action Planning | RAG Rating | Responsible party | Timescale | Comments
1 | We will use the Slalom World Championships in 2023 as a platform for social impact programmes targeted at women and girls | The Slalom World Championship delivered a successful social impacts programme as part of the underpinning event activities, and can be read about here. The #ShePaddles programme will continue as part of our standard delivery (details under Ambition 1, Action 1), and we will continue to provide support and signposting of the upskilled instructors into Club opportunities, and support Lee Valley White Water Centre with its paddling and community engagement activities. |  | Recreational Programmes Lead | N/A
2 | We will support discipline committees to develop and implement inclusion strategies and initiatives into their plans | Non-Olympic Disciplines will be supported to identify specific areas of opportunity and delivery. In Year 2, the aim will be to create a system for Disciplines to apply for financial support for projects with inclusion specific outcomes. |  | Club Support Officers Recreational Programme Lead | 2024-12-01
3 | We will encourage more people from diverse backgrounds to volunteer at competitions and events | Through the Canoe Crew, targeted communications to local and national organisations will be used to encourage a wide range of volunteers to engage with local and national events. |  | Events and Competition Officer | 2024-10-01
4 | We will implement a revised transgender competition policy (above entry level events) and support discipline committees and event organisers with implementation | We will review the Transgender Competition Policy annually, ensuring greater accessibility and inclusive language. |  | EDI Lead Director of Governance Legal and Governance Officer | 2024-01-01
|  | Communication and support around the updated policy will be rolled out through the year, including education about the policy and the eligibility process, and supporting information such as how to develop Open competition categories and changing room guidance. |  | EDI Lead Director of Governance Legal and Governance Officer | 2024-06-01
5 | We will deliver education and resources to event volunteers and supporters to further understanding of equality, diversity and inclusion topics in an event context | We will develop a training plan for volunteers, with delivery starting in 2025 |  | Competition Development Officer | 2024-11-01
Ambition 9: Focused on governance, people, equality and sustainability
Strategic action |  | Year 2 Action Planning | RAG Rating | Responsible party | Timescale | Comments
1 | We will attain and maintain compliance with the new Code for Sport Governance and Equality Standard for Sport. | We will attain compliance with the Code for Sports Governance |  | Director of Governance | 2024-03-01
|  | We will complete a final submission against Moving to Inclusion Framework |  | EDI Lead | 2024-09-01
2 | We will revise and regularly review key policies and ensure there are robust systems and processes for reporting and addressing discriminatory or exclusionary behaviour. | A policy and procedure schedule has been published, and will be adhered to throughout 2024. |  | Director of Governance/Governance Committee EDI Lead | 2024-12-01
3 | The Paddle UK Board will publish a new Board Diversity Action Plan and report annually on its delivery and the delivery of this strategy | We will review progress against Board Diversity Action Plan 2023/2024 and revise Board Diversity Action Plan |  | Director of Governance/Nominations Committee/Board | 2024-11-01
|  | We will complete a consitutional review, ensuring inclusion considerations are embedded |  | Director of Governance/Board
|  | We will collate and publish the Year 2 benchmarking report in January 2025 (collation and review will be completed by December 2024) |  | EDI Lead
4 | We will support our people to champion diversity through enhanced EDI training, staff initiatives and the establishment of effective EDI working groups, appointment of EDI Board Champion | We will deliver biannual EDI training to staff and ensure all new staff complete an EDI eLearning module as part of their induction |  | EDI Lead HR Director | 2024-12-01
|  | We will implement an EDI Board Champion Role Description |  | Director of Governance | 2024-05-01
5 | There will be an organisation-wide increase in the use of equality impact assessments on all major programmes, procurement and recruitment processes and partnership engagement to drive inclusion considerations | We will develop and deliver staff EDI training and publish resources on use of Equality Impact Assessments and demonstrate increase in use by staff across every department |  | EDI Lead | 2024-09-01
6 | We will continue to gather and consistently monitor diversity data for all staff and board recruitment | Staff data is collected through our internal People system, but is only provided voluntarily. However, we have reported on the staff demographics for the first time in our 2024 benchmarking report. |  | HR Director | 2024-12-01
|  | We will encourage staff who have not completed the Equality Monitoring Information Form in the Logbook to complete the form to enable better monitoring/prepresentation of staff diversity |  | HR Director | 2024-07-01
|  | We will gather, monitor and report on Board Diversity Data through the Nominations Committee process. |  | Director of Governance | 2024-12-01
7 | We will continue to work with the Inclusion Advisory Group and recognised organisations promoting inclusion and diversity to help us implement this strategy | We will recruit a new IAG Chair, embedding processes which aim to increase the ethnic diversity and disability representation of the IAG where possible |  | EDI Lead | 2024-06-01
We will ensure frequent (quarterly) and effective IAG meetings throughout the year and collect member feedback to ensure impact
8 | We will ensure that equality, diversity and inclusion is embedded within our People, Safeguarding and Welfare, and Sustainability strategies | We will review Equality Impact Assessments for our People, Safeguarding and Welfare, and Sustainability strategies |  | Director of Governance | 2024-09-01
|  | We will ensure inclusion is highlighted within the annual reports on delivery of our People, Safeguarding and Welfare, and Sustainability strategies |  |  | 2024-12-01
Ambition 10: Improving digital services and communications
Strategic action |  | Year 2 Action Planning | RAG Rating | Responsible party | Timescale | Comments
1 | We will launch and develop a new Paddle UK website with improved accessibility options, including across documents, other organisational websites and digital platforms | Over the last five years, the rapid growth in recreational paddling by a broader and more diverse audience has resulted in a change in the interests of our members. As a result, British Canoeing has rebranded to Paddle UK as of 13th March 2024, reflecting the more diverse membership demographics, being far more inclusive and digitially accessible, and capturing the breadth of paddling activity that falls under our responsibility. |  | Director of Business Development and Communications | March 2024 launch Work ongoing throughout 2024 to year end
|  | As part of the rebrand, we will launch a new corporate website. We will use the All in One Accessibility tool to ensure accessibility is continually reviewed. All subsidiary websites and platforms will be reviewed for screen reader accessibility. |  | Director of Digital Transformation and IT | December 2024
2 | We will enhance and develop communications plans to further support the organisation's equality, diversity and inclusion ambitions across teams, and support national and international campaigns with relevant programme leads | We will continue sharing relevant awareness days, campaigns and events through our website, newsletter and social channels as set out in our Inclusion Communications Plan. Continue sharing Paddler Spotlight and focused stories gathered through the Stronger Together Fund to suport inclusion initiatives, campaigns and awareness. Identify event opportunities to use to build a more diverse image library to be used across all channels. |  | Digital Marketing and Communications Officer Content Officer | December 2024
3 | We will share more case studies and stories to improve representation, and the diversity in imagery and content across our websites, digital platforms, social media channels, advertising and promotional materials | We will continue monthly Paddler Spotlight feature, specifically targeting current areas of under-representation, and encouraging other departments, identified individuals and stakeholders to share their stories. |  | Digital Marketing and Communications Officer | December 2024
4 | We will support staff and volunteers to showcase activity through the creation of an equality, diversity and inclusion content guide | We will use Staff News and other key stakeholder newsletters and online social groups to promote and embed the EDI Content Guide. |  | Digital Marketing and Communications Officer Content Officer | 2024-06-01
5 | There will be an organisation-wide increase in the use of equality impact assessments on all major programmes, procurement and recruitment processes and partnership engagement to drive inclusion considerations | Focussed Equality Impact Training will be delivered to staff in 2024, and we will use our end of year reporting to demonstrate the increased use and impact of these Assessments. |  | Equality, Diversity and Inclusion Lead | 2024-09-01